## Sheet1
EGN 424: Option Analysis Calculator
Version 2 - 9 May 2014
| Option 1 | Largely residential
| Option 2 | Bushland adjacent to a wetland
| Option 3 | Some residential/rural
|  |  |  | Option 1 | 14.65 |  | Option 2 | 15.8 |  | Option 3 | 16.1
| Criteria | Difference between best option and worst option |  | Relative Score (1-10) 1 - most preferred option 10 - least preferred option | Comments |  | Relative Score (1-10) 1 - most preferred option 10 - least preferred option | Comments |  | Relative Score (1-10) 1 - most preferred option 10 - least preferred option | Comments
| Capex | 3. Moderate difference |  | 1. Best option | Least cost option |  | 8 | Extra route length ~$150k |  | 10. Worst option | Extra route length ~$200k
| Opex | 4. Minor difference |  | 1. Best option | No vegetation management required |  | 10. Worst option | Most vegetation management required ~150m |  | 6 | ~100m vegetation management required
| Ecology | 2. Large difference |  | 1. Best option | No impact on vegetation |  | 10. Worst option | EEC likely to be affected, no significant clearing required |  | 9 | Access track required through bushland ~15m
| Heritage | 5. Negligible difference |  | 10. Worst option | #15 Smith Street is State Heritage listed. No direct impacts involved, overhead line will be placed on the opposite side of the street |  | 1. Best option | No heritage impacts |  | 1. Best option | No heritage impacts
| Pollution | 5. Negligible difference |  | 3 | PT located >40m from waterways and >5m from drain |  | 10. Worst option | PT located ~23m from the wetland |  | 1. Best option | PT is in a grassed paddock ~85m from the nearest drain
| Community - construction | 4. Minor difference |  | 10. Worst option | Requires a street closure and 1 night of night works. However, impacts short term. |  | 1. Best option | No disruption to residents |  | 3 | Minor disruptions to pedestrians and driveway access.
| Community - ongoing | 1. Significant difference |  | 10. Worst option | Passes 25 houses and a school |  | 1. Best option | Passes no houses |  | 2 | Passes 3 houses
|  | 1. Significant difference | 1 | 1. Best option | 1
|  | 2. Large difference | 0.75 | 2 | 2
|  | 3. Moderate difference | 0.5 | 3 | 3
|  | 4. Minor difference | 0.25 | 4 | 4
|  | 5. Negligible difference | 0.05 | 5 | 5
|  |  |  | 6 | 6
|  |  |  | 7 | 7
|  |  |  | 8 | 8
|  |  |  | 9 | 9
|  |  |  | 10. Worst option | 10
Criteria |  |  |  | Option 1 |  | Option 2 |  | Option 3 | Checking for max and min
Capex | 0.5 |  | 1 | 0.5 | 8 | 4 | 10 | 5 | 1 | 10 | 0
Opex | 0.25 |  | 1 | 0.25 | 10 | 2.5 | 6 | 1.5 | 1 | 10 | 0
Ecology | 0.75 |  | 1 | 0.75 | 10 | 7.5 | 9 | 6.75 | 1 | 10 | 0
Heritage | 0.05 |  | 10 | 0.5 | 1 | 0.05 | 1 | 0.05 | 1 | 10 | 0
Pollution | 0.05 |  | 3 | 0.15 | 10 | 0.5 | 1 | 0.05 | 1 | 10 | 0
Community - construction | 0.25 |  | 10 | 2.5 | 1 | 0.25 | 3 | 0.75 | 1 | 10 | 0
Community - ongoing | 1 |  | 10 | 10 | 1 | 1 | 2 | 2 | 1 | 10 | 0
|  |  |  | 14.65 |  | 15.8 |  | 16.1
CAUTION NOTES:
The preferred route is that option which achieves the best balance between the competing objectives. It is the option which maximises the overall attainment of all criteria taking into account their relative importance.
Given the subjective nature of selecting issues/criteria, obtaining data and assigning weightings, the process should be used as a guide only for the methodology and should only be used as one factor in making the decision. It is helpful and usually more important to ensure that all stakeholders have the opportunity to participate in the process by expressing the importance of particular factors from their perspective (refer to Ausgrid's Community Consultation Guidelines).
It may be appropriate that the final result be tested for sensitivity to both the data, and weightings. This can be achieved by changing the data and weightings within reasonable degrees of confidence. The degree to which the result changes (if at all) will represent the degree of sensitivity of the decision.
Results which have a high sensitivity should be treated with additional caution. In this instance it may be necessary to place less reliance on this process and more reliance on other methods (refer to Ausgrid's Community Consultation Guidelines).
INSTRUCTIONS
1. Add or remove options as relevant. Add a general description of each option in the field next to the options list in order to distinguish one option from another.
2. Add or remove criteria in the table as relevant.
3. Scale the criteria for all of the options in order to determine the score of each option. Each option must have a "1. Best option" and a "10. Worst option". Each option should be scored relative to the a "1. Best option" and a "10. Worst option" (ie an option which is similar to the best option would get a score of 2 or 3).
4. Refer to the calculated number (red) next to each of the options. Rank the options based on their score. The option with the overall lowest score is the preferred option.
NOTE
The difference between the "1. Best option" and "10. Worst option" is used to scale the criteria. For example, if all options pass a similar number of houses, than 'Community - ongoing' will need to be scored the same for each option and this criteria is not a critical factor in the determining the best option.